## Symposium
Planning Timeline For Symposiums
12 Months
Event Title (Date/Time)
Event Audience (Staff, Students, Alumni, Community)
Event Sponsor Package
Event Website
Event Budget
Event Venue
Form Event Committee
6 Months
Preliminary Agenda for Event
Reach Out to Potential Sponsors
Reach Out to Speakers
Create Save the Date
Create Invitation
Create Invitation Reminder
Create Zoom
Create Registration Page
Create Logistic Email for Attendees
Create Logistic Email for Speakers
Create Thank You Email
3 Months
Speakers Travel Arrangements
Outside NSU Dinner Arrangements
Marquee
Speaker Info for Website (Bios, Headshots)
1 Month
AV Request (technology needs)
Work Order (furniture needed, set up, custodial)
Catering
Call for Volunteers Email
Finalize Sponsor Monies
Upload Event Program to Website
2-3 Weeks
Directional Signs to Copy Center
Parking Signs to Copy Center
Event Program to Copy Center
Event Posters for Campus
Center Pieces
Tablecloths
Speakers Presentation for Website
1 Week
Event Dry-Run/ Walkthrough for Volunteers
Check In Supplies (pens, scissors, stapler, etc.)
Name Badges
Name Badge Holders
Table Tents
Parking Instructions
PaybyPhone Parking ID's
Directional Signs
Parking Signs
Table Cloths (logo and w/o)
Clicker
Spare Laptop
Volunteer Kits
Volunteer Assigned Sheet
Check In Sheet
Attendees Gifts (notepad, pens)
Speaker Gifts
Post-Event
Thank you Email Sent
Event Photos Posted to Flicker
Videos to SharkMedia
(CLEs) Post Certificate Online
Link Recordings to Website
Post-Event Brief Meeting

## Small Events
Planning Timeline For Events
9 Months
Event Title (Date/Time)
Event Audience (Staff, Students, Alumni, Community)
Event Sponsor Package
Event Website
Event Budget
Event Venue
Form Event Committee
6 Months
Preliminary Agenda for Event
Reach Out to Potential Sponsors
Reach Out to Speakers
Create Save the Date
Create Invitation
Create Invitation Reminder
Create Zoom
Create Registration Page
Create Logistic Email for Attendees
Create Logistic Email for Speakers
Create Thank You Email
3 Months
Speakers Travel Arrangements
Outside NSU Dinner Arrangements
Marquee
Speaker Info for Website (Bios, Headshots)
1 Month
AV Request (technology needs)
Work Order (furniture needed, set up, custodial)
Catering
Call for Volunteers Email (if applicable)
Finalize Sponsor Monies (if applicable)
Upload Event Program to Website
2-3 Weeks
Directional Signs to Copy Center
Parking Signs to Copy Center
Event Program to Copy Center
Event Posters for Campus
Center Pieces
Tablecloths
Speakers Presentation for Website
1 Week
Event Dry-Run/ Walkthrough for Volunteers (if applicable)
Check In Supplies (pens, scissors, stapler, etc.)
Name Badges
Name Badge Holders
Table Tents
Parking Instructions
PaybyPhone Parking ID's
Directional Signs
Parking Signs
Table Cloths (logo and w/o)
Clicker
Spare Laptop
Volunteer Kits
Volunteer Assigned Sheet
Check In Sheet
Attendees Gifts (notepad, pens)
Speaker Gifts
Post-Event
Thank you Email Sent
Event Photos Posted to Flicker
Videos to SharkMedia
(CLEs) Post Certificate Online
Link Recordings to Website
Post-Event Brief Meeting

## Virtual Event
Planning Timeline For Virtual Events
6-9 Months
Event Title (Date/Time)
Event Audience (Staff, Students, Alumni, Community)
Event Sponsor Package (if applicable)
Event Website
Event Budget
Event Venue (if applicable)
Form Event Committee
6 Months
Preliminary Agenda for Event
Reach Out to Potential Sponsors (if applicable)
Reach Out to Speakers
Create Save the Date
Create Invitation
Create Invitation Reminder
Create Zoom
Create Registration Page
Create Logistic Email for Attendees
Create Logistic Email for Speakers
Create Thank You Email
3 Months
Send out Save The Date
Post on Social Media, Sharkbytes, College Newsletters
Marquee
Speaker Info for Website (Bios, Headshots)
1 Month
AV Request (technology needs)
Catering
Call for Volunteers Email (if applicable)
Finalize Sponsor Monies (if applicable)
Upload Event Program to Website
Send Invitation
3 Weeks
Directional Signs to Copy Center
Event Posters for Campus
Speakers Presentation for Website
Send Invitation Reminder 1
1 Week
Event Dry-Run
Speaker Gifts
Send Invitation Reminder 2
Post-Event
Thank you Email Sent
Event Photos Posted to Flicker
Videos to SharkMedia
(CLEs) Post Certificate Online
Link Recordings to Website
Post-Event Brief Meeting

## Volunteer Sheet
EVENT NAME |  |  |  |  | Event Info
Date | Time | Name | Cell # | Role | Date | Event
MM/DD/YY | Start - End Time |  |  |  | Date | Reception
MM/DD/YY | Start - End Time |  |  |  | Date
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time |  |  |  | AM Shift | Start - End Time
MM/DD/YY | Start - End Time |  |  |  | PM Shift | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time
MM/DD/YY | Start - End Time

## Check-In
EVENT NAME
First Name | Last Name | GUEST #'s | Guest Name | VIP | Check-In

## Day Of Check-List
EVENT NAME
Item | Check
Check-In Table Supplies
Table Check-In Signs
Name Badges
Name Badge Holder
Blank Badges
Table Tents
Speaker Gifts
Volunteer Gifts
Attendee Gifts
Check-In Lists
Volunteer List
Parking Information
Parking Signs
Table Cloths
Center Pieces
Clicker
Easels
Posters
First Aid Kit
Radios
Badge Printer
Printed Programs
Catering Master Invoice
Catering Contact Info
AV Contact Info
Venue Contact Info
Standby Slides
Reception Playlist

## Budget
Create a Personal Monthly Budget in this worksheet. Helpful instructions on how to use this worksheet are in cells in this column. Arrow down to get started.
Title of this worksheet is in cell at right. Next instruction is in cell A4. | EVENT BUDGET
Projected Monthly Income label is in cell at right. Enter Income 1 in cell E4 and Extra Income in E5 to calculate Total monthly income in E6. Next instruction is in cell A6. | PROJECTED INCOME | Budget |  | 0 | PROJECTED BALANCE (Projected income minus expenses) |  |  | 0
|  | Sponsors |  | 0
Projected Balance is auto calculated in cell J4, Actual Balance in J6, and Difference in J8. Next instruction is in cell A8. |  | Total Event Income |  | 0 | ACTUAL BALANCE (Actual income minus expenses) |  |  | 0
Actual Monthly Income label is in cell at right. Enter Income 1 in cell E8 and Extra Income in E9 to calculate Total monthly income in E10. Next instruction is in cell A12. | ACTUAL INCOME | Budget |  | 0 | DIFFERENCE (Actual minus projected) |  |  | 0
|  | Sponsors |  | 0
|  | Total Event Income |  | 0
Enter details in Housing table starting in cell at right and in Entertainment table starting in cell G12. Next instruction is in cell A25. | VENUE | Projected Cost | Actual Cost | Difference | ENTERTAINMENT | Projected Cost | Actual Cost | Difference
| Space | 0 | 0 | 0 | DJ |  |  | 0
| Furniture | 0 | 0 | 0 | Other |  |  | 0
| Table Cloths | 0 | 0 | 0 | Subtotal |  |  | 0
| Center Pieces | 0 | 0 | 0
| Work Order Set Up | 0 | 0 | 0 | TBD | Projected Cost | Actual Cost | Difference
| Work Order Custodial | 0 | 0 | 0 | TBD |  |  | 0
| Other | 0 | 0 | 0 | TBD |  |  | 0
| Subtotal |  |  | 0 | TBD |  |  | 0
[5 empty] | Other |  |  | 0
| TECHNOLOGY | Projected Cost | Actual Cost | Difference | Subtotal |  |  | 0
| AV | 0 | 0 | 0
| Photography | 0 | 0 | 0 | SPONSORS | Projected Cost | Actual Cost | Difference
Enter details in Transportation table starting in cell at right and in Loans table starting in cell G24. Next instruction is in cell A35. | Videography | 0 | 0 | 0 | Sponsor 1 |  |  | 0
| Other | 0 | 0 | 0 | Sponsor 2 |  |  | 0
| Subtotal |  |  | 0 | Sponsor 3 |  |  | 0
[5 empty] | Other |  |  | 0
| MARKETING | Projected Cost | Actual Cost | Difference | Subtotal |  |  | 0
| Marquee |  |  | 0
| Invitations |  |  | 0 | GIFTS AND DONATIONS | Projected Cost | Actual Cost | Difference
| Sharkbytes |  |  | 0 | Charity 1 |  |  | 0
| Newsletter |  |  | 0 | Charity 2 |  |  | 0
| Radio |  |  | 0 | Charity 3 |  |  | 0
Enter details in Insurance table starting in cell at right and in Taxes table starting in cell G33. Next instruction is in cell A42. | Newspaper |  |  | 0 | Subtotal |  |  | 0
| Programs |  |  | 0
| Signage |  |  | 0 | OTHER (MISC.) | Projected Cost | Actual Cost | Difference
| Other |  |  | 0 | TBD |  |  | 0
| Subtotal |  |  | 0 | TBD |  |  | 0
[5 empty] | TBD |  |  | 0
| CATERING | Projected Cost | Actual Cost | Difference | Other |  |  | 0
Enter details in Food table starting in cell at right and in Savings table starting in cell G40. Next instruction is in cell A48. | Breakfast |  |  | 0 | Subtotal |  |  | 0
| Lunch |  |  | 0
| Reception |  |  | 0
| Other |  |  | 0
| Subtotal |  |  | 0 | TOTAL PROJECTED COST |  |  | 0
Enter details in Pets table starting in cell at right and in Gifts table starting in cell G46. Next instruction is in cell A56. | PROMOTIONAL ITEMS | Projected Cost | Actual Cost | Difference | TOTAL ACTUAL COST |  |  | 0
| Speaker Gifts |  |  | 0
| Volunteer Gifts |  |  | 0 | TOTAL DIFFERENCE |  |  | 0
| Attendees Gifts |  |  | 0
| Other |  |  | 0
| Subtotal |  |  | 0
Enter details in Personal Care table starting in cell at right and in Legal table starting in cell G52. Next instruction is in cell A59.
Total Projected Cost is auto calculated in cell J59, Total Actual Cost in J61, and Total Difference in J63.